## _Meta
key | value
workbook_schema_version | 0.1.0
tenant | Summit Ridge Construction Pty Ltd
functional_currency | AUD
dataset_seed | 20260814
as_of_date | 2026-07-31

## Projects
native_id | code | name | status | scenario
PRJ-001 | WHX | Westhaven Warehouse Extension | completed | healthy
PRJ-002 | MCF | Meridian Medical Centre Fitout | completed | labour_overrun
PRJ-003 | APR | Ashgrove Apartment Refurbishment | completed | late_client
PRJ-004 | MBR | Murrin Bridge Repair | active | retention_heavy
PRJ-005 | ISL | Ironbank Industrial Slab | completed | materials_overrun
PRJ-006 | SCH | Sandstone School Upgrade | active | pending_variations

## CostCodes
code | name
01-50-00 | Site Services
02-41-00 | Demolition works
03-30-00 | Concrete supply
05-12-00 | Structural steel
06-10-00 | Carpentry package
09-21-00 | Partitions and linings
09-90-00 | Painting package
22-00-00 | Hydraulic services
23-00-00 | Mechanical services
26-00-00 | Electrical services
31-23-00 | Earthworks and plant

## Activities
project_code | cost_code | name | quantity | unit | planned_start | planned_finish | progress_method
WHX | 01-50-00 | Site Services | 8 | weighted % | 2025-02-01 | 2025-11-30 | weighted_milestone
WHX | 02-41-00 | Demolition works | 6 | weighted % | 2025-02-01 | 2025-11-30 | weighted_milestone
WHX | 03-30-00 | Concrete supply | 15 | weighted % | 2025-02-01 | 2025-11-30 | weighted_milestone
WHX | 05-12-00 | Structural steel | 13 | weighted % | 2025-02-01 | 2025-11-30 | weighted_milestone
WHX | 06-10-00 | Carpentry package | 8 | weighted % | 2025-02-01 | 2025-11-30 | weighted_milestone
WHX | 09-21-00 | Partitions and linings | 10 | weighted % | 2025-02-01 | 2025-11-30 | weighted_milestone
WHX | 09-90-00 | Painting package | 6 | weighted % | 2025-02-01 | 2025-11-30 | weighted_milestone
WHX | 22-00-00 | Hydraulic services | 8 | weighted % | 2025-02-01 | 2025-11-30 | weighted_milestone
WHX | 23-00-00 | Mechanical services | 8 | weighted % | 2025-02-01 | 2025-11-30 | weighted_milestone
WHX | 26-00-00 | Electrical services | 9 | weighted % | 2025-02-01 | 2025-11-30 | weighted_milestone
WHX | 31-23-00 | Earthworks and plant | 9 | weighted % | 2025-02-01 | 2025-11-30 | weighted_milestone
MCF | 01-50-00 | Site Services | 8 | weighted % | 2025-04-01 | 2026-02-28 | weighted_milestone
MCF | 02-41-00 | Demolition works | 6 | weighted % | 2025-04-01 | 2026-02-28 | weighted_milestone
MCF | 03-30-00 | Concrete supply | 15 | weighted % | 2025-04-01 | 2026-02-28 | weighted_milestone
MCF | 05-12-00 | Structural steel | 13 | weighted % | 2025-04-01 | 2026-02-28 | weighted_milestone
MCF | 06-10-00 | Carpentry package | 8 | weighted % | 2025-04-01 | 2026-02-28 | weighted_milestone
MCF | 09-21-00 | Partitions and linings | 10 | weighted % | 2025-04-01 | 2026-02-28 | weighted_milestone
MCF | 09-90-00 | Painting package | 6 | weighted % | 2025-04-01 | 2026-02-28 | weighted_milestone
MCF | 22-00-00 | Hydraulic services | 8 | weighted % | 2025-04-01 | 2026-02-28 | weighted_milestone
MCF | 23-00-00 | Mechanical services | 8 | weighted % | 2025-04-01 | 2026-02-28 | weighted_milestone
MCF | 26-00-00 | Electrical services | 9 | weighted % | 2025-04-01 | 2026-02-28 | weighted_milestone
MCF | 31-23-00 | Earthworks and plant | 9 | weighted % | 2025-04-01 | 2026-02-28 | weighted_milestone
APR | 01-50-00 | Site Services | 8 | weighted % | 2025-06-01 | 2026-06-30 | weighted_milestone
APR | 02-41-00 | Demolition works | 6 | weighted % | 2025-06-01 | 2026-06-30 | weighted_milestone
APR | 03-30-00 | Concrete supply | 15 | weighted % | 2025-06-01 | 2026-06-30 | weighted_milestone
APR | 05-12-00 | Structural steel | 13 | weighted % | 2025-06-01 | 2026-06-30 | weighted_milestone
APR | 06-10-00 | Carpentry package | 8 | weighted % | 2025-06-01 | 2026-06-30 | weighted_milestone
APR | 09-21-00 | Partitions and linings | 10 | weighted % | 2025-06-01 | 2026-06-30 | weighted_milestone
APR | 09-90-00 | Painting package | 6 | weighted % | 2025-06-01 | 2026-06-30 | weighted_milestone
APR | 22-00-00 | Hydraulic services | 8 | weighted % | 2025-06-01 | 2026-06-30 | weighted_milestone
APR | 23-00-00 | Mechanical services | 8 | weighted % | 2025-06-01 | 2026-06-30 | weighted_milestone
APR | 26-00-00 | Electrical services | 9 | weighted % | 2025-06-01 | 2026-06-30 | weighted_milestone
APR | 31-23-00 | Earthworks and plant | 9 | weighted % | 2025-06-01 | 2026-06-30 | weighted_milestone
MBR | 01-50-00 | Site Services | 8 | weighted % | 2025-08-01 | 2026-08-31 | weighted_milestone
MBR | 02-41-00 | Demolition works | 6 | weighted % | 2025-08-01 | 2026-08-31 | weighted_milestone
MBR | 03-30-00 | Concrete supply | 15 | weighted % | 2025-08-01 | 2026-08-31 | weighted_milestone
MBR | 05-12-00 | Structural steel | 13 | weighted % | 2025-08-01 | 2026-08-31 | weighted_milestone
MBR | 06-10-00 | Carpentry package | 8 | weighted % | 2025-08-01 | 2026-08-31 | weighted_milestone
MBR | 09-21-00 | Partitions and linings | 10 | weighted % | 2025-08-01 | 2026-08-31 | weighted_milestone
MBR | 09-90-00 | Painting package | 6 | weighted % | 2025-08-01 | 2026-08-31 | weighted_milestone
MBR | 22-00-00 | Hydraulic services | 8 | weighted % | 2025-08-01 | 2026-08-31 | weighted_milestone
MBR | 23-00-00 | Mechanical services | 8 | weighted % | 2025-08-01 | 2026-08-31 | weighted_milestone
MBR | 26-00-00 | Electrical services | 9 | weighted % | 2025-08-01 | 2026-08-31 | weighted_milestone
MBR | 31-23-00 | Earthworks and plant | 9 | weighted % | 2025-08-01 | 2026-08-31 | weighted_milestone
ISL | 01-50-00 | Site Services | 8 | weighted % | 2025-10-01 | 2026-05-31 | weighted_milestone
ISL | 02-41-00 | Demolition works | 6 | weighted % | 2025-10-01 | 2026-05-31 | weighted_milestone
ISL | 03-30-00 | Concrete supply | 15 | weighted % | 2025-10-01 | 2026-05-31 | weighted_milestone
ISL | 05-12-00 | Structural steel | 13 | weighted % | 2025-10-01 | 2026-05-31 | weighted_milestone
ISL | 06-10-00 | Carpentry package | 8 | weighted % | 2025-10-01 | 2026-05-31 | weighted_milestone
ISL | 09-21-00 | Partitions and linings | 10 | weighted % | 2025-10-01 | 2026-05-31 | weighted_milestone
ISL | 09-90-00 | Painting package | 6 | weighted % | 2025-10-01 | 2026-05-31 | weighted_milestone
ISL | 22-00-00 | Hydraulic services | 8 | weighted % | 2025-10-01 | 2026-05-31 | weighted_milestone
ISL | 23-00-00 | Mechanical services | 8 | weighted % | 2025-10-01 | 2026-05-31 | weighted_milestone
ISL | 26-00-00 | Electrical services | 9 | weighted % | 2025-10-01 | 2026-05-31 | weighted_milestone
ISL | 31-23-00 | Earthworks and plant | 9 | weighted % | 2025-10-01 | 2026-05-31 | weighted_milestone
SCH | 01-50-00 | Site Services | 8 | weighted % | 2026-01-01 | 2026-12-15 | weighted_milestone
SCH | 02-41-00 | Demolition works | 6 | weighted % | 2026-01-01 | 2026-12-15 | weighted_milestone
SCH | 03-30-00 | Concrete supply | 15 | weighted % | 2026-01-01 | 2026-12-15 | weighted_milestone
SCH | 05-12-00 | Structural steel | 13 | weighted % | 2026-01-01 | 2026-12-15 | weighted_milestone
SCH | 06-10-00 | Carpentry package | 8 | weighted % | 2026-01-01 | 2026-12-15 | weighted_milestone
SCH | 09-21-00 | Partitions and linings | 10 | weighted % | 2026-01-01 | 2026-12-15 | weighted_milestone
SCH | 09-90-00 | Painting package | 6 | weighted % | 2026-01-01 | 2026-12-15 | weighted_milestone
SCH | 22-00-00 | Hydraulic services | 8 | weighted % | 2026-01-01 | 2026-12-15 | weighted_milestone
SCH | 23-00-00 | Mechanical services | 8 | weighted % | 2026-01-01 | 2026-12-15 | weighted_milestone
SCH | 26-00-00 | Electrical services | 9 | weighted % | 2026-01-01 | 2026-12-15 | weighted_milestone
SCH | 31-23-00 | Earthworks and plant | 9 | weighted % | 2026-01-01 | 2026-12-15 | weighted_milestone

## Progress
project_code | cost_code | as_of_date | pct_complete | recorded_by
WHX | 01-50-00 | 2026-07-31 | 100 | Synthetic site PM
WHX | 02-41-00 | 2026-07-31 | 100 | Synthetic site PM
WHX | 03-30-00 | 2026-07-31 | 100 | Synthetic site PM
WHX | 05-12-00 | 2026-07-31 | 100 | Synthetic site PM
WHX | 06-10-00 | 2026-07-31 | 100 | Synthetic site PM
WHX | 09-21-00 | 2026-07-31 | 100 | Synthetic site PM
WHX | 09-90-00 | 2026-07-31 | 100 | Synthetic site PM
WHX | 22-00-00 | 2026-07-31 | 100 | Synthetic site PM
WHX | 23-00-00 | 2026-07-31 | 100 | Synthetic site PM
WHX | 26-00-00 | 2026-07-31 | 100 | Synthetic site PM
WHX | 31-23-00 | 2026-07-31 | 100 | Synthetic site PM
MCF | 01-50-00 | 2026-07-31 | 100 | Synthetic site PM
MCF | 02-41-00 | 2026-07-31 | 100 | Synthetic site PM
MCF | 03-30-00 | 2026-07-31 | 100 | Synthetic site PM
MCF | 05-12-00 | 2026-07-31 | 100 | Synthetic site PM
MCF | 06-10-00 | 2026-07-31 | 100 | Synthetic site PM
MCF | 09-21-00 | 2026-07-31 | 100 | Synthetic site PM
MCF | 09-90-00 | 2026-07-31 | 100 | Synthetic site PM
MCF | 22-00-00 | 2026-07-31 | 100 | Synthetic site PM
MCF | 23-00-00 | 2026-07-31 | 100 | Synthetic site PM
MCF | 26-00-00 | 2026-07-31 | 100 | Synthetic site PM
MCF | 31-23-00 | 2026-07-31 | 100 | Synthetic site PM
APR | 01-50-00 | 2026-07-31 | 100 | Synthetic site PM
APR | 02-41-00 | 2026-07-31 | 100 | Synthetic site PM
APR | 03-30-00 | 2026-07-31 | 100 | Synthetic site PM
APR | 05-12-00 | 2026-07-31 | 100 | Synthetic site PM
APR | 06-10-00 | 2026-07-31 | 100 | Synthetic site PM
APR | 09-21-00 | 2026-07-31 | 100 | Synthetic site PM
APR | 09-90-00 | 2026-07-31 | 100 | Synthetic site PM
APR | 22-00-00 | 2026-07-31 | 100 | Synthetic site PM
APR | 23-00-00 | 2026-07-31 | 100 | Synthetic site PM
APR | 26-00-00 | 2026-07-31 | 100 | Synthetic site PM
APR | 31-23-00 | 2026-07-31 | 100 | Synthetic site PM
MBR | 01-50-00 | 2026-07-31 | 92.3 | Synthetic site PM
MBR | 02-41-00 | 2026-07-31 | 92.3 | Synthetic site PM
MBR | 03-30-00 | 2026-07-31 | 92.3 | Synthetic site PM
MBR | 05-12-00 | 2026-07-31 | 92.3 | Synthetic site PM
MBR | 06-10-00 | 2026-07-31 | 92.3 | Synthetic site PM
MBR | 09-21-00 | 2026-07-31 | 92.3 | Synthetic site PM
MBR | 09-90-00 | 2026-07-31 | 92.3 | Synthetic site PM
MBR | 22-00-00 | 2026-07-31 | 92.3 | Synthetic site PM
MBR | 23-00-00 | 2026-07-31 | 92.3 | Synthetic site PM
MBR | 26-00-00 | 2026-07-31 | 92.3 | Synthetic site PM
MBR | 31-23-00 | 2026-07-31 | 92.3 | Synthetic site PM
ISL | 01-50-00 | 2026-07-31 | 100 | Synthetic site PM
ISL | 02-41-00 | 2026-07-31 | 100 | Synthetic site PM
ISL | 03-30-00 | 2026-07-31 | 100 | Synthetic site PM
ISL | 05-12-00 | 2026-07-31 | 100 | Synthetic site PM
ISL | 06-10-00 | 2026-07-31 | 100 | Synthetic site PM
ISL | 09-21-00 | 2026-07-31 | 100 | Synthetic site PM
ISL | 09-90-00 | 2026-07-31 | 100 | Synthetic site PM
ISL | 22-00-00 | 2026-07-31 | 100 | Synthetic site PM
ISL | 23-00-00 | 2026-07-31 | 100 | Synthetic site PM
ISL | 26-00-00 | 2026-07-31 | 100 | Synthetic site PM
ISL | 31-23-00 | 2026-07-31 | 100 | Synthetic site PM
SCH | 01-50-00 | 2026-07-31 | 58.3 | Synthetic site PM
SCH | 02-41-00 | 2026-07-31 | 58.3 | Synthetic site PM
SCH | 03-30-00 | 2026-07-31 | 58.3 | Synthetic site PM
SCH | 05-12-00 | 2026-07-31 | 58.3 | Synthetic site PM
SCH | 06-10-00 | 2026-07-31 | 58.3 | Synthetic site PM
SCH | 09-21-00 | 2026-07-31 | 58.3 | Synthetic site PM
SCH | 09-90-00 | 2026-07-31 | 58.3 | Synthetic site PM
SCH | 22-00-00 | 2026-07-31 | 58.3 | Synthetic site PM
SCH | 23-00-00 | 2026-07-31 | 58.3 | Synthetic site PM
SCH | 26-00-00 | 2026-07-31 | 58.3 | Synthetic site PM
SCH | 31-23-00 | 2026-07-31 | 58.3 | Synthetic site PM

## Budgets
project_code | budget_version | status | cost_code | amount | label
WHX | 0 | approved | 01-50-00 | 118400 | Original tender
WHX | 0 | approved | 02-41-00 | 88800 | Original tender
WHX | 0 | approved | 03-30-00 | 222000 | Original tender
WHX | 0 | approved | 05-12-00 | 192400 | Original tender
WHX | 0 | approved | 06-10-00 | 118400 | Original tender
WHX | 0 | approved | 09-21-00 | 148000 | Original tender
WHX | 0 | approved | 09-90-00 | 88800 | Original tender
WHX | 0 | approved | 22-00-00 | 118400 | Original tender
WHX | 0 | approved | 23-00-00 | 118400 | Original tender
WHX | 0 | approved | 26-00-00 | 133200 | Original tender
WHX | 0 | approved | 31-23-00 | 133200 | Original tender
MCF | 0 | approved | 01-50-00 | 89600 | Original tender
MCF | 0 | approved | 02-41-00 | 67200 | Original tender
MCF | 0 | approved | 03-30-00 | 168000 | Original tender
MCF | 0 | approved | 05-12-00 | 145600 | Original tender
MCF | 0 | approved | 06-10-00 | 89600 | Original tender
MCF | 0 | approved | 09-21-00 | 112000 | Original tender
MCF | 0 | approved | 09-90-00 | 67200 | Original tender
MCF | 0 | approved | 22-00-00 | 89600 | Original tender
MCF | 0 | approved | 23-00-00 | 89600 | Original tender
MCF | 0 | approved | 26-00-00 | 100800 | Original tender
MCF | 0 | approved | 31-23-00 | 100800 | Original tender
APR | 0 | approved | 01-50-00 | 108800 | Original tender
APR | 0 | approved | 02-41-00 | 81600 | Original tender
APR | 0 | approved | 03-30-00 | 204000 | Original tender
APR | 0 | approved | 05-12-00 | 176800 | Original tender
APR | 0 | approved | 06-10-00 | 108800 | Original tender
APR | 0 | approved | 09-21-00 | 136000 | Original tender
APR | 0 | approved | 09-90-00 | 81600 | Original tender
APR | 0 | approved | 22-00-00 | 108800 | Original tender
APR | 0 | approved | 23-00-00 | 108800 | Original tender
APR | 0 | approved | 26-00-00 | 122400 | Original tender
APR | 0 | approved | 31-23-00 | 122400 | Original tender
MBR | 0 | approved | 01-50-00 | 148800 | Original tender
MBR | 0 | approved | 02-41-00 | 111600 | Original tender
MBR | 0 | approved | 03-30-00 | 279000 | Original tender
MBR | 0 | approved | 05-12-00 | 241800 | Original tender
MBR | 0 | approved | 06-10-00 | 148800 | Original tender
MBR | 0 | approved | 09-21-00 | 186000 | Original tender
MBR | 0 | approved | 09-90-00 | 111600 | Original tender
MBR | 0 | approved | 22-00-00 | 148800 | Original tender
MBR | 0 | approved | 23-00-00 | 148800 | Original tender
MBR | 0 | approved | 26-00-00 | 167400 | Original tender
MBR | 0 | approved | 31-23-00 | 167400 | Original tender
ISL | 0 | approved | 01-50-00 | 73600 | Original tender
ISL | 0 | approved | 02-41-00 | 55200 | Original tender
ISL | 0 | approved | 03-30-00 | 138000 | Original tender
ISL | 0 | approved | 05-12-00 | 119600 | Original tender
ISL | 0 | approved | 06-10-00 | 73600 | Original tender
ISL | 0 | approved | 09-21-00 | 92000 | Original tender
ISL | 0 | approved | 09-90-00 | 55200 | Original tender
ISL | 0 | approved | 22-00-00 | 73600 | Original tender
ISL | 0 | approved | 23-00-00 | 73600 | Original tender
ISL | 0 | approved | 26-00-00 | 82800 | Original tender
ISL | 0 | approved | 31-23-00 | 82800 | Original tender
SCH | 0 | approved | 01-50-00 | 123200 | Original tender
SCH | 0 | approved | 02-41-00 | 92400 | Original tender
SCH | 0 | approved | 03-30-00 | 231000 | Original tender
SCH | 0 | approved | 05-12-00 | 200200 | Original tender
SCH | 0 | approved | 06-10-00 | 123200 | Original tender
SCH | 0 | approved | 09-21-00 | 154000 | Original tender
SCH | 0 | approved | 09-90-00 | 92400 | Original tender
SCH | 0 | approved | 22-00-00 | 123200 | Original tender
SCH | 0 | approved | 23-00-00 | 123200 | Original tender
SCH | 0 | approved | 26-00-00 | 138600 | Original tender
SCH | 0 | approved | 31-23-00 | 138600 | Original tender

## Contracts
project_code | client | contract_value | payment_terms_days | claim_frequency | retention_pct | retention_release | median_days_late
WHX | Westhaven Logistics | 1480000 | 30 | monthly | 5 | practical_completion | 4
MCF | Meridian Health Group | 1120000 | 30 | monthly | 5 | practical_completion | 7
APR | Ashgrove Residential | 1360000 | 30 | monthly | 5 | practical_completion | 20
MBR | State Roads Authority | 1860000 | 45 | monthly | 10 | practical_completion | 10
ISL | Ironbank Manufacturing | 920000 | 30 | monthly | 5 | practical_completion | 5
SCH | Department of Education | 1540000 | 30 | monthly | 5 | practical_completion | 14

## ContractChanges
project_code | seq_no | description | value | status | approved_date
MCF | 1 | Approved infection-control upgrade | 78000 | approved | 2025-09-15
ISL | 1 | Approved concrete escalation | 46000 | approved | 2026-01-20
SCH | 1 | Pending asbestos remediation | 112000 | pending

## Commitments
project_code | subcontractor | cost_code | original_value | payment_terms_days | retention_pct
WHX | Precision Carpentry | 06-10-00 | 108928 | 30 | 5
WHX | Axis Interiors | 09-21-00 | 136160 | 30 | 5
WHX | PrimeCo Painting | 09-90-00 | 81696 | 30 | 5
WHX | Flowline Plumbing | 22-00-00 | 108928 | 30 | 5
WHX | Climate Mechanical | 23-00-00 | 108928 | 30 | 5
WHX | VoltEdge Electrical | 26-00-00 | 122544 | 30 | 5
MCF | Precision Carpentry | 06-10-00 | 82432 | 30 | 5
MCF | Axis Interiors | 09-21-00 | 103040 | 30 | 5
MCF | PrimeCo Painting | 09-90-00 | 61824 | 30 | 5
MCF | Flowline Plumbing | 22-00-00 | 82432 | 30 | 5
MCF | Climate Mechanical | 23-00-00 | 82432 | 30 | 5
MCF | VoltEdge Electrical | 26-00-00 | 92736 | 30 | 5
APR | Precision Carpentry | 06-10-00 | 100096 | 30 | 5
APR | Axis Interiors | 09-21-00 | 125120 | 30 | 5
APR | PrimeCo Painting | 09-90-00 | 75072 | 30 | 5
APR | Flowline Plumbing | 22-00-00 | 100096 | 30 | 5
APR | Climate Mechanical | 23-00-00 | 100096 | 30 | 5
APR | VoltEdge Electrical | 26-00-00 | 112608 | 30 | 5
MBR | Precision Carpentry | 06-10-00 | 136896 | 30 | 5
MBR | Axis Interiors | 09-21-00 | 171120 | 30 | 5
MBR | PrimeCo Painting | 09-90-00 | 102672 | 30 | 5
MBR | Flowline Plumbing | 22-00-00 | 136896 | 30 | 5
MBR | Climate Mechanical | 23-00-00 | 136896 | 30 | 5
MBR | VoltEdge Electrical | 26-00-00 | 154008 | 30 | 5
ISL | Precision Carpentry | 06-10-00 | 67712 | 30 | 5
ISL | Axis Interiors | 09-21-00 | 84640 | 30 | 5
ISL | PrimeCo Painting | 09-90-00 | 50784 | 30 | 5
ISL | Flowline Plumbing | 22-00-00 | 67712 | 30 | 5
ISL | Climate Mechanical | 23-00-00 | 67712 | 30 | 5
ISL | VoltEdge Electrical | 26-00-00 | 76176 | 30 | 5
SCH | Precision Carpentry | 06-10-00 | 113344 | 30 | 5
SCH | Axis Interiors | 09-21-00 | 141680 | 30 | 5
SCH | PrimeCo Painting | 09-90-00 | 85008 | 30 | 5
SCH | Flowline Plumbing | 22-00-00 | 113344 | 30 | 5
SCH | Climate Mechanical | 23-00-00 | 113344 | 30 | 5
SCH | VoltEdge Electrical | 26-00-00 | 127512 | 30 | 5

## CashInputs
key | value | note
opening_bank_balance | 284000 | as at 2026-08-01
forecast_start_date | 2026-08-01
payroll_fortnightly | 96500 | site + office
overhead_monthly | 42000 | head office run rate
gst_next_payment_date | 2026-08-28

## Sources
item | source | reference | notes
Transactions | Synthetic generator | Seed 20260814 | For integration testing only
Amounts | Accounting identities | AUD ex-GST plus separate GST | Not real company data