## Retention
Estimated Retention Position — Summit Ridge Construction Pty Ltd
As of 2026-08-15 · AUD · ESTIMATED from % complete — not from certified claims or a retention ledger. Release dates are planned, not certified.
Project | Client | Contract Value | % Complete | Est. Revenue Certified | Est. Client Retention | Release Trigger | Planned Release Date | Est. Sub Retention Withheld | Net Position | Status
APR — Ashgrove Apartment Refurbishment | Ashgrove Residential | 1360000 | 100% | 1360000 | 68000 | practical_completion | 2026-06-30 | 24884.31 | 43115.69 | CLAIMABLE NOW (overdue)
ISL — Ironbank Industrial Slab | Ironbank Manufacturing | 920000 | 100% | 920000 | 46000 | practical_completion | 2026-05-31 | 13717.77 | 32282.23 | CLAIMABLE NOW (overdue)
MBR — Murrin Bridge Repair | State Roads Authority | 1860000 | 92% | 1716780 | 171678 | practical_completion | 2026-08-31 | 27176.01 | 144501.99 | DUE WITHIN 90 DAYS
MCF — Meridian Medical Centre Fitout | Meridian Health Group | 1120000 | 100% | 1120000 | 56000 | practical_completion | 2026-02-28 | 20225.86 | 35774.14 | CLAIMABLE NOW (overdue)
SCH — Sandstone School Upgrade | Department of Education | 1540000 | 58% | 897820 | 44891 | practical_completion | 2026-12-15 | 17002.21 | 27888.79 | NOT YET DUE
WHX — Westhaven Warehouse Extension | Westhaven Logistics | 1480000 | 100% | 1480000 | 74000 | practical_completion | 2025-11-30 | 28817.82 | 45182.18 | CLAIMABLE NOW (overdue)
TOTAL |  | 8280000 |  | 7494600 | 460569 |  |  | 131823.98 | 328745.02