## _Meta
key | value
workbook_schema_version | 0.1.0
tenant | Northwind Construction Pty Ltd
functional_currency | AUD
prepared_by | Sample generator

## Projects
native_id | code | name | status
PRJ-01 | NGW | Northgate Warehouse | active
PRJ-02 | BAC | Bayside Aged Care | active
PRJ-03 | CVB | Clearview Bridge | active

## CostCodes
code | name
03-30-00 | Cast-in-place concrete
31-23-00 | Earthworks
05-12-00 | Structural steel
07-40-00 | Roofing & cladding
32-13-00 | Concrete paving
01-50-00 | Temporary facilities

## Activities
project_code | cost_code | name | quantity | unit | planned_start | planned_finish | progress_method
NGW | 31-23-00 | Bulk earthworks | 4500 | m3 | 2026-07-01 | 2026-07-20 | physical_qty
NGW | 03-30-00 | Slab & footings | 320 | m3 | 2026-07-10 | 2026-08-05 | physical_qty
NGW | 05-12-00 | Structural steel | 42 | t | 2026-07-25 | 2026-08-20 | physical_qty
BAC | 05-12-00 | Canopy steel | 8 | t | 2026-07-01 | 2026-07-15 | physical_qty
BAC | 07-40-00 | Cladding | 1200 | m2 | 2026-07-10 | 2026-08-10 | physical_qty
CVB | 31-23-00 | Abutment earthworks | 900 | m3 | 2026-07-05 | 2026-07-25 | physical_qty
CVB | 32-13-00 | Approach paving | 650 | m2 | 2026-07-15 | 2026-08-05 | physical_qty

## Progress
project_code | cost_code | as_of_date | pct_complete | recorded_by
NGW | 31-23-00 | 2026-07-31 | 90 | Site PM
NGW | 03-30-00 | 2026-07-31 | 35 | Site PM
NGW | 05-12-00 | 2026-07-31 | 10 | Site PM
BAC | 05-12-00 | 2026-07-31 | 80 | Site PM
BAC | 07-40-00 | 2026-07-31 | 45 | Site PM
CVB | 31-23-00 | 2026-07-31 | 60 | Site PM
CVB | 32-13-00 | 2026-07-31 | 25 | Site PM

## Budgets
project_code | budget_version | status | cost_code | amount | label
NGW | 0 | approved | 31-23-00 | 20000 | Original tender
NGW | 0 | approved | 03-30-00 | 42000 | Original tender
NGW | 0 | approved | 05-12-00 | 60000 | Original tender
BAC | 0 | approved | 05-12-00 | 12000 | Original tender
BAC | 0 | approved | 07-40-00 | 38000 | Original tender
CVB | 0 | approved | 31-23-00 | 9000 | Original tender
CVB | 0 | approved | 32-13-00 | 26000 | Original tender
BAC | 1 | approved | 07-40-00 | 44000 | Approved revision 1 — added west elevation

## Contracts
project_code | client | contract_value | payment_terms_days | claim_frequency | retention_pct | retention_release
NGW | Northgate Developments | 480000 | 30 | monthly | 5 | practical_completion
BAC | Bayside Care Group | 610000 | 45 | monthly | 5 | defects_liability_end
CVB | State Roads Authority | 390000 | 30 | monthly | 10 | practical_completion

## ContractChanges
project_code | seq_no | description | value | status | approved_date
BAC | 1 | Variation — west elevation cladding | 34000 | approved | 2026-07-12
NGW | 1 | Variation — extra roller door | 8500 | pending

## Commitments
project_code | subcontractor | cost_code | original_value | payment_terms_days | retention_pct
NGW | CivilWorks Earthmoving | 31-23-00 | 19000 | 30 | 5
BAC | Metro Roofing Co | 07-40-00 | 40000 | 30 | 5
CVB | CivilWorks Earthmoving | 32-13-00 | 25000 | 30 | 5

## CommitmentChanges
project_code | subcontractor | seq_no | description | value | status
BAC | Metro Roofing Co | 1 | West elevation add | 6000 | approved

## CashInputs
key | value | note
opening_bank_balance | 85000 | as at forecast start
forecast_start_date | 2026-08-01
payroll_weekly | 14500 | site + office
overhead_monthly | 22000 | head office run rate
gst_next_payment_date | 2026-08-28
gst_next_payment_amount | 18000 | estimated BAS